## Summary
D & B Selection Evaluation Matrix
2020-03-30
Notes: | 1. Abbreviations listed across the header of each bidder evaluation chart represent parties involved in evaluation of the RFP responses: DSC - Global Architect, Roche PM - Roche Local Project Team, TPM - Technical Project Manager for the given project.
2. This evaluation is developed based on information requested in D & B selection RFP and shall be scored based on documents submitted by bidders, except commercial quotation which will be scored after the final quotation is received.
3. Evaluation criteria are listed in column B followed by a detailed description in column C
4. Each criteria ( from B to E) should be graded on a 1 to 5 point spread, 5 being the highest score.
5. Only yellow coloured boxes are to be edited
6. Barring unforeseen circumstances, the contract will be awarded to the firm with the highest cumulative score.
7. If any changes are sought, please align with Corporate Architect team or Global Expert Program Management.
Code | Evaluation Criteria | Allocated Weightage | Bidder 1 | Bidder 2 | Bidder 3 | Bidder 4
|  |  | Weighted Score | Weighted Score | Weighted Score | Weighted Score
A | Administration | fully confirmed or not | confirmed | confirmed | confirmed | confirmed
B | Design & Creativity | 40 | 0 | 0 | 0 | 0
| Alignment with Roche Global Guidelines | 8 | 0
| Conceptual strength | 4 | 0
| Design methodology | 4 | 0
| Quality of detailing and documentation | 8 | 0
| Local code compliance | 8 | 0
| Alignment with Workplace Strategy and functional requirements | 8 | 0
C | Management and technical capabilities | 19 | 0 | 0 | 0 | 0
| Company Corporate Profile | 1 | 0
| RFP return completion and conformity | 1 | 0
| Construction administration | 1 | 0
C1 | Relevant Experience
| Office fit-out experience in given local market | 1 | 0
| Roche experience | 1 | 0
| Sustainability certified projects (LEED; WELL, BREEAM...) | 1 | 0
C2 | Delivery Team
| D&B Project Manager | 2
| Design Manager | 2
| MEP engineer | 1
| Acoustic engineer | 1
| Communication | 1
C3 | Work Methodology
| Master schedule | 1 | 0
| Poject Management | 1 | 0
D | Commercial fee | 30 | 0 | 0 | 0 | 0
E | Construction capabilities | 11 | 0 | 0 | 0 | 0
| Construction manager | 3 | #ERROR! | #ERROR! | #ERROR! | #ERROR!
| Construction method statement | 3 | #ERROR! | #ERROR! | #ERROR! | #ERROR!
| Construction schedule | 3 | 0
| Intervene to construction activity | 2 | 0
| Project specific focuses | 2 | 0
| Choice of partners in tendering/Approach to subcontractors/Management of nominated parties | 2 | 0
| Total | 100 | 0 | 0 | 0 | 0

## Bidder 1
D & B Selection Evaluation Matrix
Bidder: | Bidder 1 | [7 empty] | 2020-03-30
Notes: | 1. Abbreviations listed across the header of each bidder evaluation chart represent parties involved in evaluation of the RFP responses: DSC - Global Architect, Roche PM - Roche Local Project Team, TPM - Technical Project Manager for the given project.
2. This evaluation is developed based on information requested in D & B selection RFP and shall be scored based on documents submitted by bidders, except commercial quotation which will be scored after the final quotation is received.
3. Evaluation criteria are listed in column B followed by a detailed description in column C
4. Each criteria ( from B to E) should be graded on a 1 to 5 point spread, 5 being the highest score.
5. Only yellow coloured boxes are to be edited
6. Barring unforeseen circumstances, the contract will be awarded to the firm with the highest cumulative score.
7. If any changes are sought, please align with Corporate Architect team or Global Expert Program Management.
Administration points are mandatory and each D&B company needs to confirm that they fulfil this requirements.
A | Administration | Description | Bidder`s info
| Guarantee period (months) | -
| Form of contract | Special clauses (Closed budget + Delivery timing guaranteed
| Roche payment term | Acceptance of Roche payment terms
| Penalty system | -
| Insurance | Professional indemnity insurance
| Licencing | Licence, ISO certificates
| Financial stability | Provide annual turnover
| Compliance with local health and safety regulations | -
Code | Evaluation Criteria | Description | Recommended Weighting | Global Architect | Roche Project Team | RP | TPM | Average Score | Weighted Score | Comment
B | Design & Creativity |  | 40 | [5 empty] | 0
| Alignment with Roche Global Guidelines | Design compliance with Roche interior design guidelines/principle/specifications. Look and feel reflects corporate image and builds memorable experience to staff and visitors. Health & wellbeing elements incorporated. | 8 |  | N/A | N/A | N/A |  | 0
| Conceptual strength | Clear and consistent design concept. Strong idea/framework/foundation driving the design, giving the project direction and identity. Successful interpretation of context and local culture in design. Clarity of conceptual thinking process. | 8 |  | N/A | N/A | N/A |  | 0
| Design methodology | Client engagement and work methodology, systematic design development approach, deliverables description, quality control. Methods of managing design changes, design updates coordination. | 4 |  | N/A | N/A | N/A |  | 0
| Quality of detailing and documentation | Thorough and comprehensive construction documents, high quality of design details. | 4 |  | N/A | N/A | N/A |  | 0
| Alignment with Workplace Strategy and functional requirements | Alignment with WPS report. Reflecting WPS recommendations of activity based working and flexibility in workplace design. Functionality and space requirements are met. | 8 |  |  |  | N/A | 0 | 0
| Design quality of layout | Layout successully applies Roche interior design principles, creating a connected & balanced workplace. | 8 |  | N/A | N/A | N/A |  | 0
C | Management and technical capabilities |  | 19 | [5 empty] | 0
| Company Corporate Profile | Size, global presence, year of establishment, general market reputation | 1 |  |  |  |  | 0 | 0
| RFP return completion and conformity | Verified against RFP submission checklist | 1 | N/A |  |  |  | 0 | 0
| Local code compliance | Demonstrate familiarity with local construction codes | 1 | N/A |  | N/A |  | 0 | 0
| Construction administration | Site coordination and support during construction; management of site-related changes | 1 | N/A |  |  |  | 0 | 0
C1 | Relevant Experience
| Office fit-out experience in given local market | Relevant office fit-out experience, recently completed projects comparable in size; similar organisation is a plus | 2 |  |  |  |  | 0 | 0
| Roche experience | Roche experience (DIA/Pharma), References provided, feedback | 1 |  |  |  |  | 0 | 0
| Sustainability certified projects (LEED; WELL, BREEAM...) | Experience with design of projects accredited by LEED,WELL, BREEAM etc. | 1 | N/A |  |  |  | 0 | 0
C2 | Delivery Team
| D&B Project Manager | Proposed team organization structure, defined roles and responsibilities. Understanding of Project Objectives, Requirements & Deliverables, Local presence, Roche experience | 2 |  |  |  |  | 0 | 0
| Design Lead | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| MEP engineer | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| Acoustic engineer | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| Communication | Customer Focus & Communication, Contract discussions, presentation clarity, in-person interviews | 1 |  |  |  |  | 0 | 0
C3 | Work Methodology
| Master schedule | Rationality and alignment with Roche design and fit-out process | 3 |  |  |  |  | 0 | 0
| Poject Management | Project Management: Commitment to quality, costs, and timelines. Coordination capabilities of design team, subcontractors, and vendors. | 2 | N/A |  |  |  | 0 | 0
D | Commercial fee | only assess the total | 30 | [5 empty] | 0
| Design fee |  |  | N/A | N/A | N/A | N/A |  |  | Please indicate the fee
| Build fee |  |  | N/A | N/A | N/A | N/A |  |  | Please indicate the fee
| Transparent billing system | To be taken into consideration |  | N/A | N/A | N/A | N/A
| Total |  | 30 | N/A |  |  |  | 0 | 0
E | Construction capabilities |  | 11 | [5 empty] | 0
| Construction manager | Experience & knowledge, involvement in this project, specific relevant project experience, communication. Combination of proposal & interview. | 3 | N/A |  |  |  | 0 | 0
| Construction method statement | Construction work methods, proposed site arrangement, construction sequence, material management, logistics, safety management, workers management, etc. | 2 | N/A |  |  |  | 0 | 0
| Construction schedule | Rationality and alignment of construction schedule with master schedule. Align with procurement & delivery schedule, manpower & equipment plan, etc. | 2 | N/A |  |  |  | 0 | 0
| Project specific focus | Analysis of project specific critical issues and key risks of construction activities, with reasonable mitigations. | 2 | N/A |  |  |  | 0 | 0
| Choice of partners in tendering/Approach to subcontractors/Management of nominated parties | Appropriate methodology on management and attendance of nominated parties: landlord, nominated contractors, vendors, etc. | 2 | N/A |  |  |  | 0 | 0
| Total | - | 100 | [5 empty] | 0

## Bidder 2
D & B Selection Evaluation Matrix
Bidder: | Bidder 1 | [7 empty] | 2020-03-30
Notes: | 1. Abbreviations listed across the header of each bidder evaluation chart represent parties involved in evaluation of the RFP responses: DSC - Global Architect, Roche PM - Roche Local Project Team, TPM - Technical Project Manager for the given project.
2. This evaluation is developed based on information requested in D & B selection RFP and shall be scored based on documents submitted by bidders, except commercial quotation which will be scored after the final quotation is received.
3. Evaluation criteria are listed in column B followed by a detailed description in column C
4. Each criteria ( from B to E) should be graded on a 1 to 5 point spread, 5 being the highest score.
5. Only yellow coloured boxes are to be edited
6. Barring unforeseen circumstances, the contract will be awarded to the firm with the highest cumulative score.
7. If any changes are sought, please align with Corporate Architect team or Global Expert Program Management.
Administration points are mandatory and each D&B company needs to confirm that they fulfil this requirements.
A | Administration | Description | Bidder`s info
| Guarantee period (months) | -
| Form of contract | Special clauses (Closed budget + Delivery timing guaranteed
| Roche payment term | Acceptance of Roche payment terms
| Penalty system | -
| Insurance | Professional indemnity insurance
| Licencing | Licence, ISO certificates
| Financial stability | Provide annual turnover
| Compliance with local health and safety regulations | -
Code | Evaluation Criteria | Description | Recommended Weighting | Global Architect | Roche Project Team | RP | TPM | Average Score | Weighted Score | Comment
B | Design & Creativity |  | 40 | [5 empty] | 0
| Alignment with Roche Global Guidelines | Design compliance with Roche interior design guidelines/principle/specifications. Look and feel reflects corporate image and builds memorable experience to staff and visitors. Health & wellbeing elements incorporated. | 8 |  | N/A | N/A | N/A |  | 0
| Conceptual strength | Clear and consistent design concept. Strong idea/framework/foundation driving the design, giving the project direction and identity. Successful interpretation of context and local culture in design. Clarity of conceptual thinking process. | 8 |  | N/A | N/A | N/A |  | 0
| Design methodology | Client engagement and work methodology, systematic design development approach, deliverables description, quality control. Methods of managing design changes, design updates coordination. | 4 |  | N/A | N/A | N/A |  | 0
| Quality of detailing and documentation | Thorough and comprehensive construction documents, high quality of design details. | 4 |  | N/A | N/A | N/A |  | 0
| Alignment with Workplace Strategy and functional requirements | Alignment with WPS report. Reflecting WPS recommendations of activity based working and flexibility in workplace design. Functionality and space requirements are met. | 8 |  |  |  | N/A | 0 | 0
| Design quality of layout | Layout successully applies Roche interior design principles, creating a connected & balanced workplace. | 8 |  | N/A | N/A | N/A |  | 0
C | Management and technical capabilities |  | 19 | [5 empty] | 0
| Company Corporate Profile | Size, global presence, year of establishment, general market reputation | 1 |  |  |  |  | 0 | 0
| RFP return completion and conformity | Verified against RFP submission checklist | 1 | N/A |  |  |  | 0 | 0
| Local code compliance | Demonstrate familiarity with local construction codes | 1 | N/A |  | N/A |  | 0 | 0
| Construction administration | Site coordination and support during construction; management of site-related changes | 1 | N/A |  |  |  | 0 | 0
C1 | Relevant Experience
| Office fit-out experience in given local market | Relevant office fit-out experience, recently completed projects comparable in size; similar organisation is a plus | 2 |  |  |  |  | 0 | 0
| Roche experience | Roche experience (DIA/Pharma), References provided, feedback | 1 |  |  |  |  | 0 | 0
| Sustainability certified projects (LEED; WELL, BREEAM...) | Experience with design of projects accredited by LEED,WELL, BREEAM etc. | 1 | N/A |  |  |  | 0 | 0
C2 | Delivery Team
| D&B Project Manager | Proposed team organization structure, defined roles and responsibilities. Understanding of Project Objectives, Requirements & Deliverables, Local presence, Roche experience | 2 |  |  |  |  | 0 | 0
| Design Lead | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| MEP engineer | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| Acoustic engineer | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| Communication | Customer Focus & Communication, Contract discussions, presentation clarity, in-person interviews | 1 |  |  |  |  | 0 | 0
C3 | Work Methodology
| Master schedule | Rationality and alignment with Roche design and fit-out process | 3 |  |  |  |  | 0 | 0
| Poject Management | Project Management: Commitment to quality, costs, and timelines. Coordination capabilities of design team, subcontractors, and vendors. | 2 | N/A |  |  |  | 0 | 0
D | Commercial fee | only assess the total | 30 | [5 empty] | 0
| Design fee |  |  | N/A | N/A | N/A | N/A |  |  | Please indicate the fee
| Build fee |  |  | N/A | N/A | N/A | N/A |  |  | Please indicate the fee
| Transparent billing system | To be taken into consideration |  | N/A | N/A | N/A | N/A
| Total |  | 30 | N/A |  |  |  | 0 | 0
E | Construction capabilities |  | 11 | [5 empty] | 0
| Construction manager | Experience & knowledge, involvement in this project, specific relevant project experience, communication. Combination of proposal & interview. | 3 | N/A |  |  |  | 0 | 0
| Construction method statement | Construction work methods, proposed site arrangement, construction sequence, material management, logistics, safety management, workers management, etc. | 2 | N/A |  |  |  | 0 | 0
| Construction schedule | Rationality and alignment of construction schedule with master schedule. Align with procurement & delivery schedule, manpower & equipment plan, etc. | 2 | N/A |  |  |  | 0 | 0
| Project specific focus | Analysis of project specific critical issues and key risks of construction activities, with reasonable mitigations. | 2 | N/A |  |  |  | 0 | 0
| Choice of partners in tendering/Approach to subcontractors/Management of nominated parties | Appropriate methodology on management and attendance of nominated parties: landlord, nominated contractors, vendors, etc. | 2 | N/A |  |  |  | 0 | 0
| Total | - | 100 | [5 empty] | 0

## Bidder 3
D & B Selection Evaluation Matrix
Bidder: | Bidder 1 | [7 empty] | 2020-03-30
Notes: | 1. Abbreviations listed across the header of each bidder evaluation chart represent parties involved in evaluation of the RFP responses: DSC - Global Architect, Roche PM - Roche Local Project Team, TPM - Technical Project Manager for the given project.
2. This evaluation is developed based on information requested in D & B selection RFP and shall be scored based on documents submitted by bidders, except commercial quotation which will be scored after the final quotation is received.
3. Evaluation criteria are listed in column B followed by a detailed description in column C
4. Each criteria ( from B to E) should be graded on a 1 to 5 point spread, 5 being the highest score.
5. Only yellow coloured boxes are to be edited
6. Barring unforeseen circumstances, the contract will be awarded to the firm with the highest cumulative score.
7. If any changes are sought, please align with Corporate Architect team or Global Expert Program Management.
Administration points are mandatory and each D&B company needs to confirm that they fulfil this requirements.
A | Administration | Description | Bidder`s info
| Guarantee period (months) | -
| Form of contract | Special clauses (Closed budget + Delivery timing guaranteed
| Roche payment term | Acceptance of Roche payment terms
| Penalty system | -
| Insurance | Professional indemnity insurance
| Licencing | Licence, ISO certificates
| Financial stability | Provide annual turnover
| Compliance with local health and safety regulations | -
Code | Evaluation Criteria | Description | Recommended Weighting | Global Architect | Roche Project Team | RP | TPM | Average Score | Weighted Score | Comment
B | Design & Creativity |  | 40 | [5 empty] | 0
| Alignment with Roche Global Guidelines | Design compliance with Roche interior design guidelines/principle/specifications. Look and feel reflects corporate image and builds memorable experience to staff and visitors. Health & wellbeing elements incorporated. | 8 |  | N/A | N/A | N/A |  | 0
| Conceptual strength | Clear and consistent design concept. Strong idea/framework/foundation driving the design, giving the project direction and identity. Successful interpretation of context and local culture in design. Clarity of conceptual thinking process. | 8 |  | N/A | N/A | N/A |  | 0
| Design methodology | Client engagement and work methodology, systematic design development approach, deliverables description, quality control. Methods of managing design changes, design updates coordination. | 4 |  | N/A | N/A | N/A |  | 0
| Quality of detailing and documentation | Thorough and comprehensive construction documents, high quality of design details. | 4 |  | N/A | N/A | N/A |  | 0
| Alignment with Workplace Strategy and functional requirements | Alignment with WPS report. Reflecting WPS recommendations of activity based working and flexibility in workplace design. Functionality and space requirements are met. | 8 |  |  |  | N/A | 0 | 0
| Design quality of layout | Layout successully applies Roche interior design principles, creating a connected & balanced workplace. | 8 |  | N/A | N/A | N/A |  | 0
C | Management and technical capabilities |  | 19 | [5 empty] | 0
| Company Corporate Profile | Size, global presence, year of establishment, general market reputation | 1 |  |  |  |  | 0 | 0
| RFP return completion and conformity | Verified against RFP submission checklist | 1 | N/A |  |  |  | 0 | 0
| Local code compliance | Demonstrate familiarity with local construction codes | 1 | N/A |  | N/A |  | 0 | 0
| Construction administration | Site coordination and support during construction; management of site-related changes | 1 | N/A |  |  |  | 0 | 0
C1 | Relevant Experience
| Office fit-out experience in given local market | Relevant office fit-out experience, recently completed projects comparable in size; similar organisation is a plus | 2 |  |  |  |  | 0 | 0
| Roche experience | Roche experience (DIA/Pharma), References provided, feedback | 1 |  |  |  |  | 0 | 0
| Sustainability certified projects (LEED; WELL, BREEAM...) | Experience with design of projects accredited by LEED,WELL, BREEAM etc. | 1 | N/A |  |  |  | 0 | 0
C2 | Delivery Team
| D&B Project Manager | Proposed team organization structure, defined roles and responsibilities. Understanding of Project Objectives, Requirements & Deliverables, Local presence, Roche experience | 2 |  |  |  |  | 0 | 0
| Design Lead | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| MEP engineer | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| Acoustic engineer | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| Communication | Customer Focus & Communication, Contract discussions, presentation clarity, in-person interviews | 1 |  |  |  |  | 0 | 0
C3 | Work Methodology
| Master schedule | Rationality and alignment with Roche design and fit-out process | 3 |  |  |  |  | 0 | 0
| Poject Management | Project Management: Commitment to quality, costs, and timelines. Coordination capabilities of design team, subcontractors, and vendors. | 2 | N/A |  |  |  | 0 | 0
D | Commercial fee | only assess the total | 30 | [5 empty] | 0
| Design fee |  |  | N/A | N/A | N/A | N/A |  |  | Please indicate the fee
| Build fee |  |  | N/A | N/A | N/A | N/A |  |  | Please indicate the fee
| Transparent billing system | To be taken into consideration |  | N/A | N/A | N/A | N/A
| Total |  | 30 | N/A |  |  |  | 0 | 0
E | Construction capabilities |  | 11 | [5 empty] | 0
| Construction manager | Experience & knowledge, involvement in this project, specific relevant project experience, communication. Combination of proposal & interview. | 3 | N/A |  |  |  | 0 | 0
| Construction method statement | Construction work methods, proposed site arrangement, construction sequence, material management, logistics, safety management, workers management, etc. | 2 | N/A |  |  |  | 0 | 0
| Construction schedule | Rationality and alignment of construction schedule with master schedule. Align with procurement & delivery schedule, manpower & equipment plan, etc. | 2 | N/A |  |  |  | 0 | 0
| Project specific focus | Analysis of project specific critical issues and key risks of construction activities, with reasonable mitigations. | 2 | N/A |  |  |  | 0 | 0
| Choice of partners in tendering/Approach to subcontractors/Management of nominated parties | Appropriate methodology on management and attendance of nominated parties: landlord, nominated contractors, vendors, etc. | 2 | N/A |  |  |  | 0 | 0
| Total | - | 100 | [5 empty] | 0

## Bidder 4
D & B Selection Evaluation Matrix
Bidder: | Bidder 1 | [7 empty] | 2020-03-30
Notes: | 1. Abbreviations listed across the header of each bidder evaluation chart represent parties involved in evaluation of the RFP responses: DSC - Global Architect, Roche PM - Roche Local Project Team, TPM - Technical Project Manager for the given project.
2. This evaluation is developed based on information requested in D & B selection RFP and shall be scored based on documents submitted by bidders, except commercial quotation which will be scored after the final quotation is received.
3. Evaluation criteria are listed in column B followed by a detailed description in column C
4. Each criteria ( from B to E) should be graded on a 1 to 5 point spread, 5 being the highest score.
5. Only yellow coloured boxes are to be edited
6. Barring unforeseen circumstances, the contract will be awarded to the firm with the highest cumulative score.
7. If any changes are sought, please align with Corporate Architect team or Global Expert Program Management.
Administration points are mandatory and each D&B company needs to confirm that they fulfil this requirements.
A | Administration | Description | Bidder`s info
| Guarantee period (months) | -
| Form of contract | Special clauses (Closed budget + Delivery timing guaranteed
| Roche payment term | Acceptance of Roche payment terms
| Penalty system | -
| Insurance | Professional indemnity insurance
| Licencing | Licence, ISO certificates
| Financial stability | Provide annual turnover
| Compliance with local health and safety regulations | -
Code | Evaluation Criteria | Description | Recommended Weighting | Global Architect | Roche Project Team | RP | TPM | Average Score | Weighted Score | Comment
B | Design & Creativity |  | 40 | [5 empty] | 0
| Alignment with Roche Global Guidelines | Design compliance with Roche interior design guidelines/principle/specifications. Look and feel reflects corporate image and builds memorable experience to staff and visitors. Health & wellbeing elements incorporated. | 8 |  | N/A | N/A | N/A |  | 0
| Conceptual strength | Clear and consistent design concept. Strong idea/framework/foundation driving the design, giving the project direction and identity. Successful interpretation of context and local culture in design. Clarity of conceptual thinking process. | 8 |  | N/A | N/A | N/A |  | 0
| Design methodology | Client engagement and work methodology, systematic design development approach, deliverables description, quality control. Methods of managing design changes, design updates coordination. | 4 |  | N/A | N/A | N/A |  | 0
| Quality of detailing and documentation | Thorough and comprehensive construction documents, high quality of design details. | 4 |  | N/A | N/A | N/A |  | 0
| Alignment with Workplace Strategy and functional requirements | Alignment with WPS report. Reflecting WPS recommendations of activity based working and flexibility in workplace design. Functionality and space requirements are met. | 8 |  |  |  | N/A | 0 | 0
| Design quality of layout | Layout successully applies Roche interior design principles, creating a connected & balanced workplace. | 8 |  | N/A | N/A | N/A |  | 0
C | Management and technical capabilities |  | 19 | [5 empty] | 0
| Company Corporate Profile | Size, global presence, year of establishment, general market reputation | 1 |  |  |  |  | 0 | 0
| RFP return completion and conformity | Verified against RFP submission checklist | 1 | N/A |  |  |  | 0 | 0
| Local code compliance | Demonstrate familiarity with local construction codes | 1 | N/A |  | N/A |  | 0 | 0
| Construction administration | Site coordination and support during construction; management of site-related changes | 1 | N/A |  |  |  | 0 | 0
C1 | Relevant Experience
| Office fit-out experience in given local market | Relevant office fit-out experience, recently completed projects comparable in size; similar organisation is a plus | 2 |  |  |  |  | 0 | 0
| Roche experience | Roche experience (DIA/Pharma), References provided, feedback | 1 |  |  |  |  | 0 | 0
| Sustainability certified projects (LEED; WELL, BREEAM...) | Experience with design of projects accredited by LEED,WELL, BREEAM etc. | 1 | N/A |  |  |  | 0 | 0
C2 | Delivery Team
| D&B Project Manager | Proposed team organization structure, defined roles and responsibilities. Understanding of Project Objectives, Requirements & Deliverables, Local presence, Roche experience | 2 |  |  |  |  | 0 | 0
| Design Lead | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| MEP engineer | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| Acoustic engineer | Experience, involvement in this project, specific relevant project experience | 1 |  |  |  |  | 0 | 0
| Communication | Customer Focus & Communication, Contract discussions, presentation clarity, in-person interviews | 1 |  |  |  |  | 0 | 0
C3 | Work Methodology
| Master schedule | Rationality and alignment with Roche design and fit-out process | 3 |  |  |  |  | 0 | 0
| Poject Management | Project Management: Commitment to quality, costs, and timelines. Coordination capabilities of design team, subcontractors, and vendors. | 2 | N/A |  |  |  | 0 | 0
D | Commercial fee | only assess the total | 30 | [5 empty] | 0
| Design fee |  |  | N/A | N/A | N/A | N/A |  |  | Please indicate the fee
| Build fee |  |  | N/A | N/A | N/A | N/A |  |  | Please indicate the fee
| Transparent billing system | To be taken into consideration |  | N/A | N/A | N/A | N/A
| Total |  | 30 | N/A |  |  |  | 0 | 0
E | Construction capabilities |  | 11 | [5 empty] | 0
| Construction manager | Experience & knowledge, involvement in this project, specific relevant project experience, communication. Combination of proposal & interview. | 3 | N/A |  |  |  | 0 | 0
| Construction method statement | Construction work methods, proposed site arrangement, construction sequence, material management, logistics, safety management, workers management, etc. | 2 | N/A |  |  |  | 0 | 0
| Construction schedule | Rationality and alignment of construction schedule with master schedule. Align with procurement & delivery schedule, manpower & equipment plan, etc. | 2 | N/A |  |  |  | 0 | 0
| Project specific focus | Analysis of project specific critical issues and key risks of construction activities, with reasonable mitigations. | 2 | N/A |  |  |  | 0 | 0
| Choice of partners in tendering/Approach to subcontractors/Management of nominated parties | Appropriate methodology on management and attendance of nominated parties: landlord, nominated contractors, vendors, etc. | 2 | N/A |  |  |  | 0 | 0
| Total | - | 100 | [5 empty] | 0