## Project Directory
Roche - Project Name
Technical Project Manager
Project Manager Name ,Organisation Name |  |  |  | Project ID |  | Insert Project ID (Quickbase)
Roche Project Manager |  |  |  | Building address |  | Insert Buidling Address
Name
Project Directory
Name | Role | Entity | E-Mail |  | Phone
Elena Melёshkina | Global Expert Program Manager | Global Real Estate & Facilities | elena.meleshkina@roche.com |  | 0041 61 6820772
Thomas Woro | PMO Support | Global Real Estate & Facilities | thomas.woro@contractors.roche.com |  | 0044 7933 386956
Blanca Castañeda | Diagnostics Corporate Interior Designer | Diagnostics Division - Global Capital Investment & Real Estate | blanca.castaneda@contractors.roche.com |  | 0034 648861573
Yelena Mokritsky | Diagnostics Corporate Interior Desiner | Diagnostics Division - Global Capital Investment & Real Estate | yelena.mokritsky@contrators.roche.com |  | 0041 798484831
Christopher Christoph Rogge | Global Expert Workplace Strategy | Diagnostic Global Facility Management and Real Estate | mailto:christoph.rogge@roche.com |  | 004441 79 596 18 58
xxx xxx | Compliance Manager | Roche Diagnostics | xxx.xxx@roche.com |  | xxx xxx
xxx xxx | Director Finance & Compliance | Roche Diagnostics | xxx.xxx@roche.com |  | xxx xxx
xxx xxx | Procurement Specialist | Roche Diagnostics | xxx.xxx@roche.com |  | xxx xxx
xxx xxx | TPM | xxx xxx | xxx.xxx |  | xxx xxx

## Monthly Report Guidance Note
Roche Diagnostics | [9 empty] | Project Monthly Report | DATE - dd/mm/yyyy
Technical Project Manager | [9 empty] | Project ID | XXXXX
Technical Project Manager
Name, Company
[10 empty] | Building address | XXXXX
Roche Project Manager
Name
PROJECT SUMMARY |  |  |  |  | EXCHANGE RATE = | 0 | Roche annually fixed CHF exchange rate |  |  | LEGEND
Project provides : |  |  | Financial information: | [6 empty] | On-going as planned
Usable floor area (sqm) = | 150 |  |  | Approved Budget - Local Currency | Approved Budget (CHF) | Forecasted Final Cost (Local Currency) | Forecasted final cost (CHF) | Actual Spend (Local Currency) | Actual Spend (CHF) | Uncertain / Low manageable risk
Usable floor area (sqft) = | 1614.585 |  | Total project costs | 0 | 0 | 0 | 0 | 0 | 0 | Delayed / Major risk
Programmed information: | dd/mm/yyyy |  | PER SQM | 0 | 0 | 0 | 0 | 0 | 0
Projected Day 1: |  |  | PER FT | 0 | 0 | 0 | 0 | 0 | 0
*Please populate the planned and actual dates in the table on the right =›
PROGRAMME SUMMARY | [13 empty] | cells to be updated
KEY MILESTONES |  | TARGET COMPLETION DATE | FORECASTED COMPLETION DATE | ACTUAL COMPLETION DATE | STATUS | [6 empty] | Task |  | Start | Duration (days) | Finish
Initiation/Kick-off Meeting |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed on time
CAPEX Budget & fit-out specs |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed on time | [6 empty] | Initiation | Plan | 2019-11-01 | 0 | 2019-11-01
Designer Selection (Procurement) |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed on time | [7 empty] | Forcasted | 2019-11-01 | 0 | 2019-11-01
Designer Appointed |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed on time | [6 empty] | Designer Tender | Plan | 2019-12-02 | 14 | 2019-12-16
General Contractor Selection (Procurement) |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed on time | [7 empty] | Forecasted | 2019-12-02 | 14 | 2019-12-16
General Contractor Appointed/D&B Contractor Appointed |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed on time | [6 empty] | Design | Plan | 2020-02-20 | 121 | 2020-06-20
Layout Approval |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed on time | [7 empty] | Forecasted | 2020-02-20 | 125 | 2020-06-24
Schematic Design Approved |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed on time | [6 empty] | Constr. Works | Plan | 2020-06-21 | 198 | 2021-01-05
Developed Design Approved |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed on time | [7 empty] | Forecasted | 2020-06-25 | 198 | 2021-01-09
Submission to Authorities/Landlord |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed with delay | [6 empty] | Day 1 | Plan | 2021-06-14 | 0 | 2021-06-14
Authorities/Landlord Approval |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Completed with delay | [7 empty] | Forecasted | 2021-06-14 | 0 | 2021-06-14
Furniture Supplier Selected |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Ongoing with minor delay
Construction/Fit-out Works |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Ongoing with minor delay
Furniture Installation |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Ongoing with major delay
Site Handover |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Ongoing with major delay
Relocation |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Ongoing with major delay
Fit-out Competion/Close-out Report issued to PMO |  | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | Ongoing with major delay
RISKS
RISK ITEM | MITIGATION | Owner | BY WHEN | RATING
Risk 1: xxx | xxx | Architect | dd/mm/yyyy
Risk 2: xxx | xxx | Contractor | dd/mm/yyyy
Risk 3: xxx | xxx | TPM | dd/mm/yyyy
Risk 4: xxx | xxx | Roche PM | dd/mm/yyyy
PROGRESS THIS PERIOD
TASK COMPLETED | DUE | STUTUS | COMMENTS
Authorities/Landlord Approval | dd/mm/yyyy | Completed
Furniture Supplier Selected | dd/mm/yyyy | Ongoing
RFP documents & Layout and concepts received from D&B vendors | dd/mm/yyyy | Ongoing
Procurement calls and finalization of D&B vendor costing | dd/mm/yyyy | Delayed
Layout approval | dd/mm/yyyy | Delayed
KEY DECISIONS
DECISION NEEDED | BY WHEN | RESPONSIBLE
Key decision 1 - xxx | xx/xx/xx | Architect
Key decision 2 - xxx | xx/xx/xx | Contractor
Key decision 3 - xxx | xx/xx/xx | Contractor
Key decision 4 - xxx | xx/xx/xx | Roche Global Architect
Key decision 5 - xxx | xx/xx/xx | D&B contractor
Key decision 6 - xxx | xx/xx/xx | D&B contractor
NEXT ACTIONS - MILESTONES
TASK | DUE | WHO
Action 1 - xxx | dd/mm/yyyy | Roche PM
Action 2 - xxx | dd/mm/yyyy | Contractor
Action 3 - xxx | dd/mm/yyyy | Designer
Action 4 - xxx | dd/mm/yyyy | TPM
Action 5 - xxx | dd/mm/yyyy | WPS
Action 6 - xxx | dd/mm/yyyy
HEALTH AND SAFETY LOG
Issue | Number | Description
Number of hours worked in month
Number of incidents recorded in reporting month - Incident - Any event resulting from an unplanned act that is contrary to health and safety standards and that results in a loss of time. Add description of what an incident, accident or near miss is
Number of accidents recorded in reporting month Accident - An event that has unintentionally happned, that results in damage, injury or harm.
Number of near misses recorded in reporting month Near Miss - An event not causing harm, but has the potential to cause injury or ill healh.
| Description | Action
Findings from Principal Contractor/General Contractor SHE audits (to be undertaken monthly alongside daily walk arounds by the Site Manager), including critical SHE matters & observations
Costs (Local Currency)
Item | Description | Approved Bugdet | Contract award | Variations | Forecasted final cost | Actual (Spend) / Invoiced to Date | Comments
1.00 SOFT COSTS
1.1 | Project Manager |  |  |  | 0
1.2 | Workplace Consultant |  |  |  | 0
1.3 | Design Consultant |  |  |  | 0
1.4 | Other Consultants |  |  |  | 0
| SUBTOTAL | 0 | 0 | 0 | 0 | 0
2.00 HARD COSTS
2.1 | Interiors |  |  |  | 0 | 0
2.1.1 | Interior Partitions |  |  |  | 0 | 0
2.1.2 | Interior Doors |  |  |  | 0 | 0
2.1.3 | Raised Floor Construction |  |  |  | 0 | 0
2.1.4 | Interior Specialties |  |  |  | 0 | 0
2.1.5 | Suspended Ceiling Construction |  |  |  | 0 | 0
2.1.6 | Wall Finishes |  |  |  | 0 | 0
2.1.7 | Flooring |  |  |  | 0 | 0
2.1.8 | Ceiling Finishes |  |  |  | 0 | 0
2.1.9 | Plumbing |  |  |  | 0 | 0
2.1.10 | Heating, Ventilation, and Air Conditioning (HVAC) |  |  |  | 0 | 0
2.1.11 | Fire Protection |  |  |  | 0 | 0
2.1.12 | Electrical |  |  |  | 0 | 0
2.1.13 | Communications |  |  |  | 0 | 0
2.1.14 | Electronic Safety and Security |  |  |  | 0 | 0
2.1.15 | Fixed Furnishings |  |  |  | 0 | 0
2.1.17 | Demolition |  |  |  | 0 | 0
2.1.18 | Main contractor's preliminaries |  |  |  | 0 | 0
2.1.19 | Main contractor’s overheads and profit |  |  |  | 0 | 0
[5 empty] | 0 | 0
| SUBTOTAL | 0 | 0 | 0 | 0 | 0
3.00 CLIENT'S DIRECT COST
3.1 | Movable Furniture |  |  |  | 0 | 0
3.2 | IT |  |  |  | 0 | 0
3.3 | Moving costs |  |  |  | 0 | 0
3.4 | Other client direct costs |  |  |  | 0 | 0
| SUBTOTAL | 0 | 0 | 0 | 0 | 0
4.00 PROJECT CONTINGENCY
4.1 | Project Contingency |  |  |  | 0
PROJECT TOTAL |  | 0 | 0 |  | 0 | 0
Exclusions: -
The above costings exclude the following: -
- xxxxx IT Equipment
- xxxx Audio Visual and Video Conferencing System
-xxxx VAT
-xxxx Signage to the external façade of building
CHANGE ORDERS
CCF Description | Change Initiated By | Programme Impact (Yes/No) | Programme Impact to Original Programme (no of weeks) | Are Changes in line with Roche's Performance Fit-Out Specifications | Pending | Approved | Not Approved | Comments |  |  |  | Technical Project Manager
CCF1: | Roche Global Design Team | Yes | 0 | [8 empty] | Roche Global Design Team
CCF2: | [11 empty] | Architect / Designer
CCF3: | [11 empty] | Contractor
CCF4: | [11 empty] | Roche Project Manager
CCF5: | [11 empty] | Roche Real Estate
CCF6: | [11 empty] | Workplace Team
CCF7: | [11 empty] | Roche IT
CCF8: | [11 empty] | Yes
CCF9: | [11 empty] | No
CCF10:
Totals |  |  |  |  | 0 | 0 | 0
Note on K8: ====== ID#AAAAHVpAnMQ Mande-Woro, Tom (2020-12-02 15:01:58) Roche Diagnostics Team will confirm the Project ID no
Note on G17: Please confirm Exchange Rate for project location with PMO Support (Tom Woro). Exchange Rate to align with Roche’s rate.
Note on A27: Key milestones within the 'Programme Summary' to include the below key milestones. Please include milestones which are aligned to your project. If you believe that a specific milestone should be amended or does not align with your proramme please highlight and review with Tom Woro (PMO Support)
Note on C27: Target Completion Date must remain the same as the original agreed project programme. Only the Actual Completion Date should be amended throughout the duration of the project to align with the actual project progress.
Note on D27: Forecasted Completion Date should be amended throughout the duration of the project to align with forecasted/revised project date.
Note on E27: Actual Completion Date should be the date the actual task was completed.
Note on F27: The RAG status within the status column should illustrate if the completion date of the task will impact the programme if not completed on time. See status descriptions below.
Note on A62: Key decision section to include project decisions required from Roche internal Project Team . i.e. Roche IT, Roche Architect, Roche Legal, Roche Workplce, Roche PM
Note on A89: Project Cost Breakdown to align with Omniclass cost breakdown below. If you believe that a specific cost description should be amended or does not align with the below item list, please highlight and review with PMO Support (Tom Woro)
Note on B99: Interior Partitions include the following: - Interior fixed partitions - Interior glazed partitions - Interior demountable partitions - Interior operable partitions - Interior screens - Interior partition supplementary components
Note on B100: Interior Doors includes the following: - Interior swinging doors - Interior entrance doors - Interior sliding doors - Interior folding doors - Interior coiling doors - Interior panel doors - Interior special function doors - Interior access doors and panels - Interior supplementary components
Note on B101: Raised Floor Construction includes the following: - Access Flooring - Platform/Stage Floors
Note on B102: Interior Specialties includes the following: - Interior railings and handrails - Interior louvers - Information specialities - Compartments and cubicles -Service walls -Wall & door protection - Toilet, bath, and laundry accessories - Interior gas lighting - Fireplaces and stoves - Safety specialties - Storage specialities
Note on B103: Suspended Ceiling Construction includes the following: - Acoustical Suspended Ceilings - Specialty suspended ceilings - Special function suspended ceilings - Ceiling suspension components
Note on B104: Wall finishes include the following: - Tile wall finish - Wall panelling - Wall coverings - Wall carpeting - Stone facing - Special wall surfacing - Wall painting and coating - Acoustical wall treatment - Wall finish supplementary components
Note on B105: Flooring includes the following: - Flooring treatment - Tile flooring - Specialty flooring - Masonry flooring - Wood flooring - Resilient flooring - Terrazzo flooring - Fluid-Applied flooring - Carpeting - Athletic flooring - Entrance flooring - Flooring supplementary components
Note on B106: Ceilin Finishes includes the followin: - Plaster and Gypsum Board Finish - Ceiling Paneling - Ceiling Painting and Coating - Acoustical Ceiling Treatment - Ceiling Finish Supplementary Components
Note on B107: Plumbing includes the following: - Domestic water distribution - Sanitary drainage - Building support plumbing systems - Process support plumbing systems
Note on B108: Heating, Ventilation and Air Conditioning (HVAC) includes the following: - Facility fuel systems - Heating systems - Cooling systems - Facility HVAC distribution systems - Ventilation - Special purpose HVAC systems
Note on B109: Fire protection includes the following: - Fire suppression - Fire protection specialities
Note on B110: Electrical includes the following: - Facility power generation - Electrical service and distribution - General purpose electrical power - Lighting - Miscellaneous electrical systems
Note on B111: Communications includes the following: - Data communications - Voice communications - Audio-Video communication - Distributed communications and monitoring
Note on B112: Electrical safety and security includes the following: - Access control and intrusion detection -Electronic surveillance - Detection and alarm - Electronic monitoring and control - Electronic safety and security supplementary components
Note on B113: Fixed Furnishings includes the following: - Fixed art - Window treatments - Casework - Fixed multiple seating - Other fixed furnishings
Note on A137: Change Orders: Change Order section to be updated as required and commentary to include information on the responsible/impacted Party and an explanation if the change order was/was not approved.

## Photos
SITE:
Project Photos
PHOTO 1 | PHOTO 2
Description | Description
PHOTO 3 | PHOTO 4
Description | Description
PHOTO 5 | PHOTO 6
Description | Description
PHOTO 7 | PHOTO 8
Description | Description
PROJECT MANAGEMENT
& CONSULTANCY