## Summary
TYPICAL PROJECT PROCESS: ARCHITECT/DESIGNER SELECTION & DESIGN
Phases
PHASE | DESCRIPTION
Architect or D&B Selection | Beginning with project Kick-off through Designer/Architect award. Refer to Arch. Selection diagram for detailed breakdown of activities
Design & Documentation | Beginning with Archictect Appointment and Kick-off through completion of Construction Documents. Refer to Design & Construction diagram for detailed breakdown of activities
Negotiations & Tender | Bidding & Negotiation through Contract Signing
Construction | Design implementation
Concept Designer + D&B
Medium Size & Complexity Project
PHASE | DURATION | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
Architect/Designer Selection | 7 wks | bar: 1 to 7
Concept and Basis of Design | 10 wks | bar: 8 to 17
Negotiations & Tender | 4 wks | bar: 18 to 21
Schematic & Developed Design | 10 wks | bar: 22 to 31
Construction | 12 wks | bar: 32 to 43
Traditional model- with MSA Designer
Large / High Complexity Project
PHASE | DURATION | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Architect/Designer Selection | 7 wks | bar: 1 to 7
Design & Documentation | 25 wks | bar: 8 to 32
Negotiations & Tender | 4 wks | bar: 33 to 36
Construction | 16 wks | bar: 37 to 52
Traditional model - standard
Large / High Complexity Project
PHASE | DURATION | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55
Architect/Designer Selection | 10 wks | bar: 1 to 10
Design & Documentation | 25 wks | bar: 11 to 35
Negotiations & Tender | 4 wks | bar: 36 to 39
Construction | 16 wks | bar: 40 to 55
D&B single phase
Small / Low Complexity Project
PHASE | DURATION | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
D&B Selection, Tender and Negotiation | 6 wks | bar: 1 to 6
Design & Documentation | 10 wks | bar: 7 to 16
Construction | 10 wks | bar: 14 to 23

## Arch. Selection
TYPICAL DESIGNER/ARCHITECT SELECTION
Phases & Process Steps
PHASE | DESCRIPTION
Establish Project Criteria | Project Kick-off with Global Architect, TPM and project team
Market Research & Longlist | Evaluation of potential candidates from prequalified list of global partners, or within local market with a goal of establisthing a longlist
Longlist Evaluations | Global Architect compiles a longlist - reviews with local team and TPM
RFI Request & Response | TPM conducts an RFI process in order to guage interest and capabilities of potential firms
Shortlist Reccomendation | Global Architect proposes a shortlist - reviews with local team and TPM; team confirms final shortlist for tender
RFP Preparation | TPM prepares tender package - reviews with local team and Global architect
RFP Request & Response | TPM conducts a formal tender process with shortlisted firms
RFP Evaluation | RFP responses are analysed and evaluation matrix is completed by the Global Architect, TPM, and local team
Architect/Designer Award & Kick-off | Architectural/Design firm is awarded, a Kick-off meeting is held for process review
Traditional model: Project Designer Selection
Large / High Complexity Project
PHASE | DURATION | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Establish Project Criteria | 1 wk | bar: 1
Market Research & Longlist | 2 wks | bar: 1 to 2
Longlist Evaluations | 1 wk | bar: 2
RFI Request & Response | 2 wks | bar: 3 to 4
Shortlist Reccomendation | 1 day
RFP Preparation | 2 wks | bar: 4 to 5
RFP Request & Response* | 3 wks | bar: 6 to 8
RFP Evaluation | 1 wk | bar: 9
Final Negotiations** | 1 wk | bar: 10
Architect/Designer Award & Kick-off | 1 day
*note: time period can vary from 2 weeks to 3 based on size of project and RFP requirements
**note: time period can vary based on local requirements
2-Stage D&B + CD model: Concept Designer Selection***
Medium Size & Complexity Project
PHASE | DURATION | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Establish Project Criteria & Shortlist | 1 wk | bar: 1
RFP Preparation | bar: 2 to 3
RFP Request & Response* | bar: 4 to 5
RFP Evaluation | bar: 6
Final Negotiations** | bar: 7
Architect/Designer Award & Kick-off
*note: time period can vary from 2 weeks to 3 based on size of project and RFP requirements
**note: time period can vary based on local requirements
***note: same process applies to Traditional Model with MSA Designer
D&B single phase model: D&B Selection
Small Project / Low Complexity
PHASE | DURATION | 1 | 2 | 3 | 4 | 5 | 6
Establish Project Criteria | 1 wk | bar: 1
Market Research & Longlist | 2 wks | bar: 1 to 2
Longlist Evaluations | 1 wk | bar: 2
Shortlist Reccomendation | 1 Day
RFP Preparation | 1 wk | bar: 2
RFP Request & Response | 2 wk | bar: 3 to 4
RFP Evaluation | 1 wk | bar: 5
Final Negotiations** | 1 wk | bar: 6
Architect/Designer Award & Kick-off | 1 day
*note: time period can vary from 2 weeks to 3 based on size of project and RFP requirements
**note: time period can vary based on local requirements

## Design & Construction
TYPICAL DESIGN TIMELINES
Phases & Process Steps
| PHASE | [8 empty] | DESCRIPTION
Concept Design & Layout
| Kick-Off | [8 empty] | On-Boarding / Research /Client Workshops. Concurrent development of concepts and layouts based on findings
| Layout & Concept, Basis of Design | [8 empty] | Concept for zoning and layout options, Design Concept with 3D views and basis of design for architectural elements, materiality, lighting, furniture, greenery, etc.
| Layout & Concept: Reviews & Revisions | [8 empty] | Reviews by local team, WPS team, and corporate architect. Account for revisions to be incorporated into layout to address comments
Schematic Design
| Schematic Development | [8 empty] | Material Selections, Material allocation by area, Ceiling plans and Lighting selections, Furniture selections and plans, plant selections and allocations, 3D views, elevations and other deliverables as needed
| SD Reviews & Revisions | [8 empty] | Reviews by local team and corporate architect. Account for revisions to be incorporated to address comments.
| SD Cost Estimate | [8 empty] | Schematic Design is validated against agreed-upon budget
Developed (Detailed) Design
| Architectural Design Development | [8 empty] | Detailed development and documentation of approved design including all elements and matrials by space type, elevations, details, and other deliverables as needed
| DD Reviews & Revisions | [8 empty] | Reviews by local team and corporate architect. Account for revisions to be incorporated after each review.
| Furniture | [8 empty] | Furniture Basis of Design Package; preparation for tender. Partially to run concurrently with DD
| Furniture Reviews & Revisions | [8 empty] | Reviews by local team and corporate architect. Account for revisions to be incorporated
| Signage | [8 empty] | Complete Signage Package. Partially to run concurrently with DD
| Signage Reviews & Revisions | [8 empty] | Reviews by local team and corporate architect. Account for revisions to be incorporated
| DD Cost Estimate | [8 empty] | Developed Design is validated against agreed-upon budget
| Tender Documentation | [8 empty] | Set of Construction Documents to be used for permits and General Contractor / D&B tender
| Contractor Bidding & Negotiation | [8 empty] | Tender process, negotiations with GC / D&B teams
| Construction | [8 empty] | Design implementation
Traditional model - standard
Large / High Complexity Project
PHASE | ACTIVITIES | DURATION |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
Concept Design (6 wks) | Kick-Off |  | 2 wks | bar: 1 to 2
| Layout / Concept & Review |  | 5 wks | bar: 2 to 6
Schematic Design (6 wks) | Schematic Development & Review |  | 5 wks | bar: 7 to 11
| SD Cost Estimate |  | 2 wks | bar: 11 to 12
Developed (Detailed) Design (8 wks) | Detailed Design Development & Review |  | 6 wks | bar: 13 to 18
| Furniture & Review |  | 7 wks | bar: 14 to 20
| Signage & Review |  | 5 wks | bar: 16 to 20
| DD Cost Estimate |  | 2 wks | bar: 19 to 20
| Tender Documentation |  | 6 wks | bar: 20 to 25
| Bidding & Negotiation |  | 4 wks | bar: 26 to 29
| Construction |  | 16 wks | bar: 30 to 45
[10 empty] | Endorsement | [5 empty] | Endorsement | [5 empty] | Approval |  | Approval
D&B single phase
Small Project / Low Complexity
PHASE | ACTIVITIES | DURATION |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Concept Design (4 wks) | Kick-Off |  | 1 wks | bar: 1
| Layout / Concept & Review |  | 4 wks | bar: 1 to 4
Schematic+Developed Design (6 wks) | Design Development & Review |  | 4 wks | bar: 5 to 8
| Furniture & Review |  | 4 wks | bar: 7 to 10
| Signage & Review |  | 3 wks | bar: 8 to 10
| SD + DD Cost Estimate |  | 2 wks | bar: 9 to 10
| Construction |  | 10 wks | 5: Endorsement
[12 empty] | Approval |  | Approval
Concept Designer + D&B
Medium Size & Complexity Project
PHASE | ACTIVITIES | DURATION |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Concept Design (10 wks) | Kick-Off, Layout & Concept |  | 4 wks | bar: 1 to 4
| Developed Concept & Basis of Design |  | 6 wks | bar: 4 to 9
| Tender Documentation |  | 2 wks | bar: 9 to 10
| Bidding & Negotiation |  | 4 wks | bar: 11 to 14
Schematic Design (4 wks) | Schematic Development & Review |  | 4 wks | bar: 15 to 20
| SD Cost Validation |  | 2 wks | bar: 19 to 20
Developed (Detailed) Design (4 wks) | Detailed Design Development & Review |  | 4 wks | bar: 21 to 26
| Furniture & Review |  | 4 wks | bar: 21 to 26
| Signage & Review |  | 2 wks | bar: 25 to 26
| DD Cost Validation |  | 2 wks | bar: 25 to 26
| Construction |  | 12 wks | bar: 27 to 38
[8 empty] | Endorsement |  |  |  |  | Approval | [10 empty] | Approval | [5 empty] | Approval

## Design Approval Process
TYPICAL DESIGN APPROVAL PROCESS
Steps & Deliverables
Applicable to Concept/Layout, Schematic Design, and Developed (Detailed) Design phases
STEP | ACTIVITIES | DURATION IN DAYS |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Deliveable | Designer issuance: deliverable to project team |  | 0 days
Review | Global Architect review & feedback |  | 1-3 days | bar: 1 to 2
Revision | Designer revision of presentation |  | 3-5 days | bar: 3 to 5
Deliveable | Designer issuance: deliverable to project team |  | 0 days
Review | Global Architect review & endorsement |  | 1 day | bar: 6
Presentation & Review | Presentation to local team/stakeholders, review and feedback or approval |  | 5 days | bar: 7 to 11
Revision | If required: Designer revision of presentation |  | 3-5 days | bar: 12 to 14
Deliveable | If required: Designer issuance: deliverable to project team |  | 0 days | 1: Deliverable; 3: Feedback; 6: Deliverable; 7: GA Endorsement, Presentation to local stakeholders; 12: Feedback or Approval
Review | If required: final approval by local stakeholders |  | 2 days | bar: 15 to 16
[18 empty] | Deliverable |  | Approval