## Fit-Out Tech PM Evaluation
| Scoring card | more than 4.0 | 5% fee bonus |  |  |  | Project Name
|  | between 2-4 points | No fee deduction |  |  |  | TPM name
|  | between 1-2 points | 10% fee deduction
#757
| SCORE | KPI DESCRIPTION | Frequency of measurement | Measurement source | QUESTIONS |  | Score (1-5) | Weighting | Comments
20%
| FINANCIAL SCORE (20%) | Budget Planned vs. Actual (20%) How much does the planned budget vary from actual budget? (budget variations can be taken into consideration in line 10 if approved by Roche) "5 = >5% below budget 4 = 1% - 5% below budget 3 = On budget 2 = 1% - 5% above budget 1 = < 5% above budget " | after project completion | final project close out report document | Planned Budget (Project CAPEX local currency) |  | 500000
[5 empty] | Roche Initiated Scope Change Variation |  | 25000
[5 empty] | Actual Project Cost (Final project cost local currency) |  | 600000
[5 empty] | Deviation Actual Project Cost minus (Planned Budget + Roche Initiated Variations) |  | 75000
[5 empty] | Reason for deviation? |  | 14.2857 |  | Sustainability
Reasoning for Variation Please attach change order log to report
1 |  | Financial Score (0-5) |  |  |  |  | 1 | 20% | 0.2
| TIMING SCORE (20%) | Schedule Planned vs. Actual (20%) How much the initial fit-out schedule varies from the actual schedule (Timeline changes occurred due to the change of scope to be taken into consideration in row 17)5 = >5% below schedule 4 = 1% - 5% below schedule 3 = On schedule 2 = 1% - 5% above schedule 1 = < 5% above schedule (all in weeks) | after project completion | final project close out report document | Initial schedule (weeks) |  | 12
[5 empty] | Roche Initiated Variation or Force-majeur Duration |  | 0
[5 empty] | Actual schedule (weeks) |  | 10
[5 empty] | Deviation |  | -2
[5 empty] | Reason for Variation? |  | -16.6667 |  | Organisation
1 |  | Timing Score (0-5) |  |  |  |  | 5 | 20% | 1
| QUALITY SCORE (20%) | Compliance with Fit-Out Specifications (10%) 5 = Exceeded expectations 4 = Performed well 3 = Performed satisfactorily 2 = Performed below average 1 = Performed poorly | After project completion | Roche Corporate Architect feedback | How much does the executed design comply with the Roche fit-out performance specification? |  | 4 | 5% | 0.2
|  |  | After project completion | PMO | Has the TPM completed the 3 endorsement stages required for the fit-out spec process? | 0.5 | 3 | 5% | 0.15
|  |  | After project completion | PMO | Has the TPM made efforts to be compliant with Roche fit-out specifications? | 0.5 | 3 | 5% | 0.15
|  | Compliance with Roche Playbook & Governance (10%) Ensure governance, controls and approvals are maintained 5 = Exceeded expectations 4 = Performed well 3 = Performed satisfactorily 2 = Performed below average 1 = Performed poorly | After project completion | PMO Healthcheck on a monthly basis | Are the mandatory activities being undertaken and mandatory tools employed? |  | 4 | 5% | 0.2
1 |  | Compliance Score | [6 empty] | 0.7
| HEALTH & SAFETY SCORE (20%) | Did the PM ensure readyness to proceed with site activity (this includes insurance, permits, H&S management plan) (5%) 5 = Exceeded expectations 4 = Performed well 3 = Performed satisfactorily 2 = Performed below average 1 = Performed poorly | At beginning of construction | PMO Healthcheck on a monthly basis | Did the TPM ensure and evidence 'readiness to proceed' step from playbook? |  | 4 | 5% | 0.2
|  | Compliance with Roche H&S guidelines and SHE Directives (5%) 5 = Exceeded expectations 4 = Performed well 3 = Performed satisfactorily 2 = Performed below average 1 = Performed poorly | monthly | PMO Healthcheck on a monthly basis | Did the TPM ensure (and evidence) that they and all parties under their supervision were briefed on the Roche Fit-Out Construction Safety manual and the local SHE guidelines? |  | 3 | 5% | 0.15
0.25
0.25
|  | Goal Zero (10%) Did the project achieve Zero reportable incidents? "5 = Project runs with full 'Goal Zero' 0 = Project incurs a recordable injury" | after project completion | final project completion report document | Were there any 'reportable' incidents? | 0.5 | 5 | 10% | 0.5
|  | Health & Safety Score | [6 empty] | 0.85
| CUSTOMER SATISFACTION SCORE (20%) | Customer Satisfaction Survey Score (20%) The overall Roche (local and HQ) satisfaction on the delivered TPM services 5= Exceeded expectations 4= Performed well 3= Performed satisfactorily 2= Perfomed below average 1= Performed poorly | after project completion | Roche local company survey | Customer Satisfaction Survey Score (1-5) - Update with the points score
|  | Customer Satisfaction Score (0-5) |  |  |  |  | 4 | 20% | 0.8
| Total Technical PM Score (0-5) | [5 empty] | 5 = Exceeded expectations 4 = Performed well 3 = Performed satisfactorily 2 = Performed below average 1 = Performed poorly |  | 3.55
Note on F10: ====== ID#AAAAN1uGaCo (2021-08-10 18:43:24) Approved Roche changes can be included here
Note on F13: ====== ID#AAAAN1uGaCw (2021-08-10 18:43:24) This helps Roche PMO identify trends
Note on F17: ====== ID#AAAAN1uGaCs (2021-08-10 18:43:24) Client approved changes and their time impact plus unforseen events can be included
Note on F20: ====== ID#AAAAN1uGaCk (2021-08-10 18:43:24) This helps Roche PMO identify trends
Note on F28: ====== ID#AAAAN1uGaC0 (2021-08-10 18:43:24) E.g. TPM to demonstrate how the Safety manual was integrated into project process
Note on F31: ====== ID#AAAAN1uGaCc (2021-08-10 18:43:24) This is a yes or no answer; Roche expect their TPMs to demonstrate Safety leadership. Reportable incidents are defined as: Any event resulting from an unplanned act that is contrary to health and safety standards and that results in a loss of time.
Note on F33: ====== ID#AAAAN1uGaCg (2021-08-10 18:43:24) Roche local provide feedback on TPM performance

## User satisfaction survey
NEW QUESTIONNAIRE TO BE ADDED
1 to 5
Please indicate the name of the Technical Project Management consultant (TPM): company name and and the name of the lead TPM
How well the TPM Partner demonstrated understanding of Global Real Estate & Facility Mangement fit-out processes?
How well did the TPM understand project requirements and ensure their implementation?
Please rate availability, responsiveness and communication skills of the TPM
Please rate the TPM`s efforts to ensure project completion on time
Please rate the TPM`s efforts to ensure project completion on budget
Please rate your overall satisfaction with the TPM consultant performance and their vallue add for the fit-out project?
To help us understand how effective the TPM was on your project and the areas for improvement, could you please add a comment with regard to the TPM performance?
Comment:
3. User Satisfaction – Defects
What was the condition of the facility with respect to defects at the time of handover?
Totally defective | Major defects | Some defects | Very limited defects | Minor defects, eliminated within 1 week
| major impact | with some impact | with no
| on users | on users | significant impact
on users
1 | 2 | 3 | 4 | 5
Comment:
4. User Satisfaction – Comments
a. Do you have any suggestions to improve the service provided by consultants/contractors?
b. Do you have any other comments in respective of the project?

## Kopie von Fit-Out Projects Revi (hidden)
Scoring card | more than 5.0 points | 5% fee bonus
| between 2.8 - 4.9 points | No fee deduction
| between 0 - 2.7 points | 10% fee deduction
SCORE | KPI DESCRIPTION | QUESTIONS |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
FINANCIAL SCORE (20%) | Budget Planned vs. Actual (20%) How much does the planned budget varies from actual budget (COs due to the change of scope should not be included) | Planned Budget (Project CAPEX as per AP2) |  | 12
|  | Actual Budget (Final project budget CHF) |  | 13
|  | Deviation |  | 8.333% | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell]
| Financial Score (0-10) |  |  | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell]
TIMING SCORE (20%) | Schedule Planned vs. Actual (20%) How much the initial fit-out schedule varies from the actual schedule (Timeline changes occurred due to the change of scope to be taken into consideration) | Initial timeline (weeks) |  | 12
|  | Actual timeline (weeks) |  | 13
|  | Deviation |  | 8.333% | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell]
|  | Did the Tech PM analyse and agree the schedule of works with the Contractors within the agreed period? |  | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown]
|  | Did the Tech PM ensure that works were completed as per the agreed schedule? |  | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | Yes: with minor exceptions | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown]
|  | Did the Tech PM submit the schedule updates? |  | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown]
|  | Deviation Score | 0.25 | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell]
|  |  | 0.25 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | 0.25 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 8 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | 0.25 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Timing Score (0-10) |  |  | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell]
QUALITY SCORE (30%) | Compliance with Fit-Out Specifications (15%) How much does the executed design comply with the Roche fit-out performance specification | Were the Roche Fit-Out Specifications filled out properly in the beginning of the project? |  | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown]
|  | How much does the executed design comply with the Roche fit-out performance specification? |  | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | Not compliant at all | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown]
|  |  | 0.25 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | 0.25 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Customer Satisfaction Survey Score (15%) The overall Roche (local and HQ) satisfaction on the delivered TPM services | Customer Satisfaction Survey Score (0-10) | 0.5 | 6
| Compliance Score (0-10) |  |  | 3 | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell]
HEALTH & SAFETY SCORE (30%) | Compliance with Roche K and SHE Directives (15%) | Did the Tech PM ensure that they and all parties under his supervision complied with Roche Health and Safety guidelines as well as with the local SHE guidelines? |  | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown]
|  | Did the Tech PM ensure compliance with Roche directives K18, K21, K6? |  | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown] | [Select Dropdown]
|  |  | 0.33 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | 0.34 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| TRIR (Total Recordable Incident Rate) (15%) Organization’s safety performance by calculating the number of recordable incidents per 100 people | 0 = 10 >0.1 – 1.0 = 4 >1.0 – 2.0 = 2 >2.1 = 0 | 0.33 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
TRIR Total (TRIR = N x 200.000 / H) N = Number of recordable incidents H = Total man-hours worked on project by all workers in a year
| Health & Safety Score (0-10) |  |  | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3
Technical PM |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total Technical PM Score |  |  |  | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell] | [Do not write / Automatic cell]
Based on:
https://docs.google.com/spreadsheets/d/1CB9wkTzit87FktYbT9vXaiImYIDlwVfS/edit#gid=711361622
https://drive.google.com/file/d/1vRzvsTxsriKQzkjmbwM3pbj5kEnaOHHI/view?ts=5e5673a3
| Interval | Points awarded
Financial Score | Above (including) 10.01% savings | 10
| Between (including) 9.01% and 10% savings | 9
| Between (including) 7.01% and 9% savings | 8
| Between (including) 5.01% and 7% savings | 7
| Between (including) 0.01% and 5% savings | 6
| On budget | 5
| Between (including) 0.01% and 5% overspend | 4
| Between (including) 5.01% and 7% overspend | 3
| Between (including) 7.01% and 9% overspend | 2
| Between (including) 9.01% and 10% overspend | 1
| Above (including) 10.01% overspend | 0
| Interval | Points awarded
Timming Score | Above (including) 10.01% time savings | 10
| Between (including) 9.01% and 10% time savings | 9
| Between (including) 7.01% and 9% time savings | 8
| Between (including) 5.01% and 7% time savings | 7
| Between (including) 0.01% and 5% time savings | 6
| On time | 5
| Between (including) 0.01% and 5% overtime | 4
| Between (including) 5.01% and 7% overtime | 3
| Between (including) 7.01% and 9% overtime | 2
| Between (including) 9.01% and 10% overtime | 1
| Above (including) 10.01% overtime | 0
| Answer | Points awarded
Dropdowns | Yes: always ¦ Yes: entirely ¦ Fully compliant | 10
| Yes: with minor exceptions ¦ Minor (not critical) deviations | 8
| Only sometimes ¦ Minor (but critical) deviations | 4
| Not really: with major exceptions ¦ Major deviations | 2
| No: never ¦ No: not at all ¦ Not compliant at all | 0